## test_plan
Test Plan: SoftPAC
Task Number | Task Description | Expected duration in (DAYS:HOURS) | Start Date | End Date | Person Responsible | Final Status (in progress/ done/ not done)
1 | Understanding BRD (Business Requirement Document) | 0:06 | 2018-06-21 | 2018-06-21 | Team Effort | done
2 | Exploring the application | 0:03 | 2018-06-21 | 2018-06-21 | Team Effort | done
4 | Creating scenarios for Member |  | 2018-06-21 | 2018-06-21 | Rajesh, Akansha | done
5 | Creating scenarios for Individual Customer |  | 2018-06-21 | 2018-06-21 | Nehal | done
6 | Creating scenarios for Company (Customer) |  | 2018-06-21 | 2018-06-21 | Himanshi | done
7 | Creating scenarios for Farmer | 0:02 | 2018-06-21 | 2018-06-21 | Harsh Jain | done
8 | Creating scenarios for Banking Services |  | 2018-06-21 | 2018-06-21 | Rajat Pancholy | done
9 | Creating scenarios for Process Flow |  | 2018-06-21 | 2018-06-21 |  | done
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66

## scenario(s)
SoftPAC Test Scenarios
Scenario ID | Scenario Name | Pre-Conditions | Scenario Description | Post-Conditions | Requirement Reference | Assumptions | Priority | Remarks
TS_001 | User Registration | User must open the website in web browser | User must be able to register on SoftPAC application by providing the following mandatory details: | User must be registered successfully | Document> Description > Scope of Testing > I. Member Registration | Not Applicable
Creating scenarios for member Registration
TS_002 | Membership registration | User is logged in | Bank staff must be able to register new member as: A: Individual B: Non-Individual | Member should be registered successfully | Document> Description > Scope of Testing > I. Member Registration | Not Applicable
Ending scenarios for Member Registration
Creating scenarios for member Modification
TS_003 | Membership Modification | User is logged in | Bank staff must be able to modify details of new member as: A:Individual B:non individual | Member details should be modified successfully | Document> Description > Scope of Testing > I. Member Registration | Not Applicable
Ending scenarios for member Modification
Creating scenerios for uploading documents
TS_004 | Uploading documents | User is logged in. | Bank Staff must be able to upload the required documents | Documents must be uploaded successfully and confirmation message should be displayed | Document> Description > Scope of Testing > I. Member Registration > upload documents | Not Applicable
Ending scenarios for uploading documents
Creating Scenarios for Transaction
TS_006 | Transaction/Transaction Entry | User is logged in | Verify that user is able to credit/debit under Transaction Entry> Receipt/Payment section. | Staff must be able to view the transaction. | Document> Description > Scope of Testing > Functions Transaction Entry
Ending scenarios for Transaction
Creating Scenarios for Term Deposit
TS_007 | Term Deposit/Fixed Deposit | User is logged in | Verify the user is able to perform the following actions: 1. Create Fixed Deposit 2. Close Fixed Deposit 3. View Fixed Deposit | User must be able to create/close/view the Fixed Deposit successfully. | Document> Description > Scope of Testing > III. Term Deposit
Ending scenarios for Term Deposit

## Case-TS_001
Test Case- TS_001
Test case ID | Author | Requirement ID | Scenario ID | Pre-Conditions | Test Case Description | Test Step Number | Test Step Description | Input Values | Expected Result | Actual Result | Status (in progress/ done/ not done) | Priority | Considered for Automation? (Yes/No)
TC_001 | Himanshi | N/A | TS_001 | Internet is working properly | Verify that staff member is successfully able to login the website | 1 | User opens the website in new browser |  |  |  | Done
TC_001 | Aakanksha Panwar | N/A | TS_002 | User must open the website in web browser | Verify member is able to register as individual or non individual | 1 | Click on the individual/non individual under member registration |  | Registration Form opens up by clicking respective registration |  | Done
[6 empty] | 2 | If individual, fill mandatory details under following sections: a.Personal b.Verification c.Address d.Other
[6 empty] | 3 | If non individual, then fill mandatory details under following sections: a.Company b.Verification d.Other
TC_003 | Himanshi | N/A | TS_002 | Internet is working properly and staff must be logged in | Verify that staff member is able to register a new member as an individual as a customer | 1 | Staff person moves the mouse over membership tab. |  |  |  | Done
[6 empty] | 2 | He clicks on individual under member registration section |  | Member Registration Individual page should open.
[6 empty] | 3 | Under personal tab, he fills the following mandatory details of member: 1. Type- Customer 2. Account Type 3. Name 4. Gender 5. DOB 6. Religion 7. Occupation 8. Caste 9. Class(Member) 10. Nationality 11. Father Name/Husband Name 12. Mother Name
[6 empty] | 4 | Under verification tab, he fills the following mandatory details of member: 1. PAN Number 2. Voter ID 3. Driving License 4. Passport/Ration Card No. 5. Aadhar ID
[6 empty] | 5 | Under address tab, he fills the following mandatory details of member: 1. Address Line 1 2. Address Line 2 3. Village Name 4. State 5. PIN Code 6. Landline 7. Mobile Number 8. Email
[6 empty] | 6 | Under others tab, he fills the following mandatory details of member: 1. Income 2. Education 3. Marital Status 4. Nature of Activity
[6 empty] | 7 | User clicks on Submit |  | Member details should be successfully submitted and upload photo page should open
[6 empty] | 8 | User selects member id of customer to upload photo
[6 empty] | 9 | He uploads photo of member and clicks on submit |  | "Image uploaded successfully" message should be displayed and user should be redirected to a page to upload signature
[6 empty] | 10 | User selects member id of customer to upload signature
[6 empty] | 11 | He uploads signature of member and clicks on submit |  | Member should be successfully registered.
TC_004 | Himanshi |  | TS_002 | Internet is working properly and staff must be logged in | Verify that staff member is able to register a new member as an individual as a member | 1 | Staff person moves the mouse over membership tab. |  |  |  | Done
[6 empty] | 2 | He clicks on individual under member registration section |  | Member Registration Individual page should open.
[6 empty] | 3 | Under personal tab, he fills the following mandatory details of member: 1. Type- Member 2. Account Type 3. Name 4. Gender 5. DOB 6. Religion 7. Occupation 8. Caste 9. Class(Member) 10. Nationality 11. Father Name/Husband Name 12. Mother Name
[6 empty] | 4 | Under verification tab, he fills the following mandatory details of member: 1. PAN Number 2. Voter ID 3. Driving License 4. Passport/Ration Card No. 5. Aadhar ID
[6 empty] | 5 | Under address tab, he fills the following mandatory details of member: 1. Address Line 1 2. Address Line 2 3. Village Name 4. State 5. PIN Code 6. Landline 7. Mobile Number 8. Email
[6 empty] | 6 | Under others tab, he fills the following mandatory details of member: 1. Income 2. Education 3. Marital Status 4. Nature of Activity
[6 empty] | 7 | User clicks on Submit |  | Member details should be successfully submitted and upload photo page should open
[6 empty] | 8 | User selects member id of customer to upload photo
[6 empty] | 9 | He uploads photo of member and clicks on submit |  | "Image uploaded successfully" message should be displayed and user should be redirected to a page to upload signature
[6 empty] | 10 | User selects member id of customer to upload signature
[6 empty] | 11 | He uploads signature of member and clicks on submit |  | Member should be successfully registered.
TC_005 | Himanshi |  | TS_002 | Internet is working properly and staff must be logged in | Verify that staff member is able to register a new member as non-individual | 1 | Staff person moves the mouse over membership tab. |  |  |  | Done
[6 empty] | 2 | He clicks on non-individual under member registration section |  | Member Registration Non-Individual page should open.
[6 empty] | 3 | Under company tab, he fills the following mandatory details of member: 1. Type- Customer 2. Account Type(Single/Joint) 3. Name 4. Operator 1 5. Operator 2 6. Constitution 7. Occupation 8. Document Details 9. Name of document 10. Issuing Authority 11. Place of Issue 12. Registration Number 13. Date of Incorporation
[6 empty] | 4 | Under verification tab, he fills the following mandatory details of member: 1. PAN Number 2. Address Line 1 3. Address Line 2 4. Village Name 5. State 6. PIN Code 7. Landline 8. Mobile Number 9. Email
[6 empty] | 5 | Under others tab, he fills the following mandatory details of member: 1. Income 2. Education 3. Marital Status 4. Nature of Activity
[6 empty] | 6 | User clicks on Submit |  | Member details should be successfully submitted and upload photo page should open
[6 empty] | 7 | User selects member id of customer to upload photo
[6 empty] | 8 | He uploads photo of member and clicks on submit |  | "Image uploaded successfully" message should be displayed and user should be redirected to a page to upload signature
[6 empty] | 9 | User selects member id of customer to upload signature
TC_006 | Harsh |  | TS_003 | Internet is working properly and staff must be logged in | Verify that staff member is able to modify member details under member modification tab | 1 | Staff person moves the mouse over membership tab. |  |  |  | Done
[6 empty] | 2 | user clicks on individual under member modification section |  | "Member modify Individual" page should open.
[6 empty] | 3 | user must select an member ID in order to choose the individual's information to modify
[6 empty] | 4 | Under personal tab, he modifies the following mandatory details of member: 1. Type- Member 2. Account Type 3. Name 4. Gender 5. DOB 6. Religion 7. Occupation 8. Caste 9. Class(Member) 10. Nationality 11. Father Name/Husband Name 12. Mother Name
[6 empty] | 5 | Under verification tab, he modifies the following mandatory details of member: 1. PAN Number 2. Voter ID 3. Driving License 4. Passport/Ration Card No. 5. Aadhar ID
[6 empty] | 6 | Under address tab, he modifies the following mandatory details of member: 1. Address Line 1 2. Address Line 2 3. Village Name 4. State 5. PIN Code 6. Landline 7. Mobile Number 8. Email
[6 empty] | 7 | Under others tab, he modifies the following mandatory details of member: 1. Income 2. Education 3. Marital Status 4. Nature of Activity
[6 empty] | 8 | User clicks on Submit |  | Member details should be successfully modified and upload photo page should open
[6 empty] | 9 | User selects member id of customer to upload photo
[6 empty] | 10 | He uploads photo of member and clicks on submit |  | "Image uploaded successfully" message should be displayed and user should be redirected to a page to upload signature
[6 empty] | 11 | User selects member id of customer to upload signature
[6 empty] | 12 | He uploads signature of member and clicks on submit
[6 empty] | 13 | User must select "confirm" from the dropdown menu from the tab actions and later on must submit. |  | Member's information should get successfully modified.
TC_007 | Harsh |  | TS_003 | Internet is working properly and staff must be logged in | Verify that staff member is able to modify member (non-individual) details under member modification tab | 1 | Staff person moves the mouse over membership tab. |  |  |  | Done
[6 empty] | 2 | user clicks on Non-individual under member modification section |  | "Member modify Non-individual" page should open.
[6 empty] | 3 | user must select an member ID in order to choose the Non-individual's information to modify
[6 empty] | 4 | Under personal tab, he modifies the following mandatory details of member: 1. Type- Member 2. Account Type 3. Name 4. Gender 5. DOB 6. Religion 7. Occupation 8. Caste 9. Class(Member) 10. Nationality 11. Father Name/Husband Name 12. Mother Name
[6 empty] | 5 | Under verification tab, he modifies the following mandatory details of member: 1. PAN Number 2. Voter ID 3. Driving License 4. Passport/Ration Card No. 5. Aadhar ID
[6 empty] | 6 | Under address tab, he modifies the following mandatory details of member: 1. Address Line 1 2. Address Line 2 3. Village Name 4. State 5. PIN Code 6. Landline 7. Mobile Number 8. Email
[6 empty] | 7 | Under others tab, he modifies the following mandatory details of member: 1. Income 2. Education 3. Marital Status 4. Nature of Activity
[6 empty] | 8 | User clicks on Submit |  | Member details should be successfully modified and upload photo page should open
[6 empty] | 9 | User selects member id of customer to upload photo
[6 empty] | 10 | He uploads photo of member and clicks on submit |  | "Image uploaded successfully" message should be displayed and user should be redirected to a page to upload signature
[6 empty] | 11 | User selects member id of customer to upload signature
[6 empty] | 12 | He uploads signature of member and clicks on submit
[6 empty] | 13 | User must select "confirm" from the dropdown menu from the tab actions and later on must submit. |  | Member's information should get successfully modified.
TC_008 |  | Nehal | TS_006 | User shoud be logged in. | Verify whether a confirmed member is able to transact using an account | 1 | User moves the mouse over transaction tab. | NA | Transactions with Confirmed accounts are operational |  | Done | N/A | Yes
[6 empty] | 2 | user clicks on Transaction Entry under Transaction section
[6 empty] | 3 | click on Receipt/payment
[6 empty] | 4 | Fill the following mandatory details a. member id b. account number c. transaction type d. transaction code e. amount f. Instrument Type
[6 empty] | 5 | click on submit
TC_009 |  | Nehal | TS_006 | User shoud be logged in. | Verify that user is able to credit/debit using Transaction Entry>Receipt Payment | 1 | move to the transaction tab | NA | Transactions can happen with multiple accounts at the same time |  | Done | N/A | Yes
[6 empty] | 2 | move to transaction entry .
[6 empty] | 3 | click on Receipt/payment
[6 empty] | 4 | Fill details under a. Member id b. Account number c. Transaction type d. Transaction code e. Amount f. No. Of Multiple Account g. Instrument Type
[6 empty] | 5 | Click on show
[6 empty] | 6 | Fill details under Enter account no : Amount :
[6 empty] | 7 | Click on done
[6 empty] | 8 | Click on submit
TC_0010 |  | Harsh | TS_006 | User shoud be logged in. | Verify both credit and debit option are available on the same page. | 1 | move to the transaction tab | NA | Credit and debit options are available on the transaction entry page |  | Done | N/A | Yes
[6 empty] | 2 | move to transaction entry .
[6 empty] | 3 | move to Receipt/payment
[6 empty] | 4 | Fill details under a. member id b. account number c. transaction type as credit d. transaction code e. amount f. Instrument Type
[6 empty] | 5 | click on submit
[6 empty] | 6 | Fill details under a. member id b. account number c. transaction type as debit d. transaction code e. amount f. Instrument Type
[6 empty] | 7 | click on submit
TC_0011 | Aakanksha Panwar | N/A | TS_007 | User must open the website in web browser and click Term Deposit. | To verify that staff is able to enter the term deposit window. | 1 | Click on the Term Deposit and further staff is able to access fields under Fixed deposit: 1. Create FD 2. View FD 3. Close FD |  | Staff is able to create,view and close FD. |  | Done
[6 empty] | 2 | Under create FD,staff is able to enter following details: 1. Member ID 2.Source Account 2.a) must be able to view balance 3.Customer Type(normal/senior citizen) 4.FD Type 4.a) if joint, fill joint holder name,relation 5.Nominee Name 6.Relation(hidden/disclose) 7.Deposit Amount View Interest Rate(interest slab and rate) 8.Tenure 9.Applicable Interest Rate 10.select Interest Pay Plan 11.Maturity Amount 12.Maturity Date 13.Transfer Fund To 14.Select Instruction 15.Account For Maturity click on submit button
[6 empty] | 3 | Under View FD, select the member ID to view the created FD.
[6 empty] | 4 | Under close FD, 1. Select the action(add,confirm) 2.Select Member ID 3.Select Account Number 4.Deposit Amount 5.App Interest Rate 6.Maturity Amount 7.Maturity Date 8.Accrue Interest 9.Transfer Fund To 10.Closure Date 11.Premature Amount 12.Penalty charge 13.Total Closure Amount